## Kev
Task (Front end) | Time (hours) | Comment
Be familiar with Spotify API and Riot API | 3
Graphically design the layout of the website | 1
Implement Database Connectors | 0.5
Make a Spotify login system more scalable | 1
Implement a summoner name search bar that works across different browsers | 1
Connent the data with backend to return champion ID from summoner name | 1
Implement a text bar to display the name of the current champion | 0.5
Make the playlist display more scalable | 1

## Perry
Task (Database) | Estimate
Implement Riot API calls to return champion ID from summoner name | 0.5
Use champion ID to fetch static playlist link | 0.5
Use champion ID to fetch champion key words/inspiration songs to generate playlists | 0.5
Return viable playlists | 0.5
Generate database with champion IDs, names, playlists, and key words | 2

## Nathan
Task (Backend) | Estimated time (hrs) | Comments
Implement Database Connectors | 0.5
Implement Spotify Backend connections | 1
Implement OAuth integration | 3
Integrate OAuth with Spotify API | 1 | Will need to rewrite dummy auth keys into actual OAuth objects
Implement Riot API calls to return champion ID from summoner name | 0.5
Use champion ID to fetch static playlist link | 0.5
Use champion ID to fetch champion key words/inspiration songs to generate playlists | 0.5
Return viable playlists | 0.5
Generate database with champion IDs, names, playlists, and key words | 2
Implement playlist display | 1.5
Implement Spotify integration | 2

## Main
Task | Time | User Story #1
implement spotify login system | 2
Implement OAuth integration | 3
Integrate OAuth with Spotify API | 1
implement summoner name search bar | 1
Implement Database Connectors | 0.5
Implement Spotify Backend connections | 1